## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Set up the basic structure of the Flask application | MUST HAVE | Flask Framework | Ayinala Koteswararao | Completed
S1 | S1 | US-001 | Design the Streamlit-based interface for the chatbot | MUST HAVE | Streamlit Framework | Ayinala Koteswararao | Completed
S2 | S2 | US-001 | Integrate Groq API for AI-powered responses | MUST HAVE | Groq API, Python | Ayinala Koteswararao | Completed
S2 | S2 | US-001 | Develop database schema and setup MySQL integration | MUST HAVE | MySQL, Flask SQLAlchemy | Ayinala Koteswararao | Completed
S3 | S3 | US-001 | Add conversational context to the chatbot responses | MUST HAVE | BERT, Sentence Transformers | Ayinala Koteswararao | Completed
S3 | S3 | US-001 | Build user registration and authentication system | MUST HAVE | Flask-Login, MySQL | Ayinala Koteswararao | Completed
S4 | S4 | US-001 | Add file upload feature for patient reports | MUST HAVE | Werkzeug, Flask | Ayinala Koteswararao | Completed
S4 | S4 | US-001 | Create additional pages | MUST HAVE | HTML, CSS | Ayinala Koteswararao | Completed
S5 | S5 | US-001 | Implement security for API keys and sensitive data | MUST HAVE | Python Dotenv | Ayinala Koteswararao | Completed
S6 | S6 | US-001 | Deploy application using Flask in LocalHost | MUST HAVE | AWS / Streamlit Sharing | Ayinala Koteswararao | Completed
S7 | S7 | US-001 | Perform rigorous testing for various edge cases | MUST HAVE | Test Cases, Groq API | Ayinala Koteswararao | Completed
S8 | S8 | US-001 | Finalize UI/UX design and deploy the production build | MUST HAVE | Frontend Enhancements | Ayinala Koteswararao | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 152 | 41 | 36 | 28 | 25 | 19 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Set up Flask application | 9-Dec-24 | 11-Dec-24 | Ayinala Koteswararao | Development | Completed | 8 | 3 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TID-01 | Design Streamlit-based chatbot interface | 12-Dec-24 | 14-Dec-24 | Ayinala Koteswararao | UI/UX Design | Completed | 10 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TID-01 | Integrate Groq API for chatbot responses | 15-Dec-24 | 18-Dec-24 | Ayinala Koteswararao | Integration | Completed | 12 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TID-01 | Database schema setup and MySQL integration | 19-Dec-24 | 22-Dec-24 | Ayinala Koteswararao | Database Design | Completed | 14 | 4 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TID-01 | Add conversational context to chatbot responses | 23-Dec-24 | 29-Dec-24 | Ayinala Koteswararao | NLP Implementation | Completed | 20 | 4 | 4 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | TID-01 | Build user authentication system | 30-Dec-24 | 3-Jan-25 | Ayinala Koteswararao | Development | Completed | 15 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | TID-01 | Add file upload feature for patient reports | 4-Jan-25 | 8-Jan-25 | Ayinala Koteswararao | Feature Development | Completed | 12 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | TID-01 | Create Home,Login,Register&index pages | 9-Jan-25 | 13-Jan-25 | Ayinala Koteswararao | Frontend Design | Completed | 10 | 3 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | TID-01 | Implement security for API keys and sensitive data | 14-Jan-25 | 18-Jan-25 | Ayinala Koteswararao | Security | Completed | 14 | 4 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | TID-01 | Deploy application using Flask In The LocalHost | 19-Jan-25 | 23-Jan-25 | Ayinala Koteswararao | Deployment | Completed | 12 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | TID-01 | Perform rigorous testing for edge cases | 24-Jan-25 | 2025-01-25 | Ayinala Koteswararao | Testing | Completed | 15 | 4 | 4 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | TID-01 | Optimize chatbot model for speed and accuracy | 2025-01-26 | 2025-01-28 | Ayinala Koteswararao | Optimization | Completed | 10 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 4 | Difficulty understanding user requirements for chatbot design | Conducted a requirements gathering workshop with stakeholders to clarify expectations.
Sprint 1 | Day 8 | Unfamiliarity with integrating third-party APIs | Referred to API documentation and conducted hands-on practice sessions to build expertise.
Sprint 2 | Day 11 | Errors in setting up the database schema for the project | Reviewed database design with a mentor and corrected schema inconsistencies.
Sprint 3 | Day 15 | Delays in implementing user authentication features | Collaborated with the team to divide tasks and expedite the development process.
Sprint 4 | Day 20 | UI inconsistencies across different screen resolutions | Conducted cross-platform testing and fixed UI responsiveness issues.
Sprint 5 | Day 25 | Challenges in optimizing model predictions for faster responses | Utilized advanced machine learning techniques and fine-tuned model parameters for better results.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2024-12-09 | 2024-12-15 | Ayinala Koteswararao | Focus on API integration | Delaying code reviews | Sharing progress regularly | Conducted hands-on practice sessions for API usage.
2 | Sprint 2 | 2024-12-16 | 2024-01-21 | Ayinala Koteswararao | Testing features more rigorously | Ignoring minor bugs | Collaborating with mentors | Scheduled a team debugging session to resolve persistent errors.
3 | Sprint 3 | 2024-12-22 | 2024-12-27 | Ayinala Koteswararao | Documenting workflow improvements | Skipping retrospective meetings | Prioritizing critical tasks | Created documentation templates for improved consistency.
4 | Sprint 4 | 2024-12-28 | 2025-01-02 | Ayinala Koteswararao | Tracking UI responsiveness issues | Assuming browser compatibility | Cross-platform testing | Resolved UI inconsistencies for different screen resolutions.
5 | Sprint 5 | 2025-01-03 | 2025-01-08 | Ayinala Koteswararao | Optimizing model performance | Postponing optimization tasks | Improving communication | Utilized advanced ML techniques to fine-tune model accuracy.
6 | Sprint 6 | 2025-01-09 | 2025-01-04 | Ayinala Koteswararao | Conducting user feedback sessions | Neglecting user feedback | Enhancing system usability | Integrated user feedback into the design process.
7 | Sprint 7 | 2025-01-20 | 2025-01-28 | Ayinala Koteswararao | Planning long-term scalability | Overlooking scalability concerns | Strengthening team collaboration | Developed a roadmap for scaling the application.